## Workstrand 1
Changing Lives Through Sport and Physical Activity
Workstrand 1: Direct 1-2-1 Development Support |  |  | Week Comm |  |  |  |  | Month
Ref | Activity | Responsibility | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | October | November | December | January | February | March | April | May | June | July | August | September
1 | Contact Award | TRT
2 | Commissioning meeting | TRT / CM
3 | Agreements in place | All
4 | Informal OP and stakeholder briefing | SM
5 | Confirm KPIs and reporting schedule
6 | Agree eligibility criteria
7 | Develop initial resources
8 | Test diagnostic tool
9 | Identify 15 client organisations
10 | Undertake needs assessment using tool
11 | Agree support requirements
12 | Allocate subject matter experts
13 | Deliver suppport to client organisations
14 | Internal partnership dialogue
15 | Quarterly activity report
16 | Quarterly update with OP
17
TRT | The Robertson Trust
OP | Operational Partners
CM | CEIS Contract Manager
CEIS | CEIS adviser
SEA | Social Enteprise Academy advisers
SP | Spartans
M | Movement
EU | Edinburgh University

## Workstrand 2
SEI Introduction to Tendering
[5 empty] | Week Comm |  |  |  | Month
Ref | Activity | Responsibility | Pre Contract Period | Contract Start Date | week 1 | week 2 | week 3 | week 4 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
1 | Contact award Letter | Buyer
2 | Allocate resources
3 | Identify new premises
4 | Brief current staff
5 | Prepare job descriptionsfor new staff
6 | Upgrade IT equipment
7 | Inform supply chain
8 | Purchase new equipment
9 | Meet with the Buyer | All | bar: Week Comm week 1
10 | Agreements in place | bar: Week Comm week 2
11 | Set Measurement Indicators | bar: Week Comm week 2
12 | Agree reporting schedule | bar: Week Comm week 2
13 | Agree payment shedule | bar: Week Comm week 2
14 | Agree communication channels | bar: Week Comm week 2
15 | Ongoing meetings with buyers | bar: Week Comm week 4; Month Month 4; Month Month 7; Month Month 10
16 | Add Activities appropriate to the contract
17
18
19
20
Legend | The area in pale bue highlights potential mobilisation activity - these are just a few ideas to start with.
Tip | List the key tasks in you will need to undertake to delvier this service in column B
Allocate responsibility in column C this could be more that one person
Use column D onwards to indicate when the task should occur